## Sheet1
Team Name: |  | AceRadiantYgor
Story Point to Hours Conversion: |  | 4 | <-- Change this value based upon your own calculations
Cost per hour: |  | 65
Velocity: |  | 4.5 | <-- 3 hours a week of work X Team size (3) X 2 weeks = 18 hours / 4 = 4.5
| As a | I want to | So that I can | Relative Estimate | Costs
1 | Team Member | Capture/Maintain basic project information | Facilitate information collection. | 1 | 260
2 | Team Member | Maintain a list of team members assigned to the project | Track estimated and actual times for each team member. | 0.5 | 130
3 | Team Member | Capture/Maintain the product backlog including relative estimates (and estimated costs) | Establish a benchmark for comparison purposes. | 1 | 260
4 | Team Member | Identify which user stories are going to be included in a given Sprint | Have an understanding what user stories will be part of a planned Sprint. | 3 | 780
5 | Team Member | Capture/Maintain subtasks for each user story that is included in a Sprint Plan | Have a detailed understanding of the work to be completed within the current Sprint. | 5 | 1300
6 | PMO | Generate a Summary report for each team member based upon actual hours worked by User Story | Understand the contributions of each team member. | 3 | 780
7 | PMO | Generate a Sprint summary report (that reports the status, time spent, and any re-estimates for each user story and it’s related subtasks. | Understand the progress that is being made as it relates to the project deliverables. | 5 | 1300
8 | Team Member | Copy any incomplete user stories (and only incomplete subtasks) from a completed sprint to a future sprint | Minimize the amount of information that needs to be moved from one Sprint to another. | 3 | 780
9 | PMO | Create a dashboard to display critical percentages associated with the project | Have a better understanding of the quality of my estimates and efficiency of my project team. | 5 | 1300
10 | Team Member/PMO | Authenticate users of the application using an email address and password | Ensure that only authorized users are able to use the application. | 3 | 780
|  |  |  | 29.5 | 7670